## Welcome
Welcome!!
Project Workflow and Journal Description:
I created this Project Workflow and Journal Excel Worksheet as a comprehensive, one-stop resource to document and showcase my organization and process throughout the Advanced Data Analytics Professional Certificate program. This worksheet is designed to track and manage all aspects of my capstone project, providing clear visibility into each phase of the project’s lifecycle.
The worksheet includes:
Project Workflow:
A structured overview of the project stages, outlining key milestones and objectives for each phase.
Action Items:
Detailed tasks and initiatives for every stage of the capstone project, ensuring that all necessary steps are tracked and completed in an organized manner.
Email Records:
Copies of important emails, along with follow-up tasks derived from these interactions, to maintain clear correspondence and ensure that all stakeholder expectations are met.
Deliverables:
Links to all project deliverables, making it easy to access and review completed work.
For optimal viewing, each worksheet is meant to be viewed at 90% zoom. As I progress through the Advanced Data Analytics Professional Certificate, this worksheet will continue to evolve, capturing the ongoing development of my project and reflecting my commitment to a structured and methodical approach to data analytics.

## C1_Tasks
Course 1: Project Proposal
Assignment Goal:
Plan your project by considering your audience, teammates, key milestones, and overall project goal, and create a project proposal for the data team.
Action Items: |  | Comments:
Create a Email Word Template to store all future emails | Completed | Use this Word template to copy and paste all emails onto for future reference. Obviously if this was a real world scenario you would not do this for privacy reasons.
Course 1 PACE Strategy Workflow Document | Completed | Plan your project while considering your audience members, teammates, key milestones, and overall project goal.
Create a project proposal for the data team. | Completed | Condensed Summary on next worksheet. | [ Completed Project Proposal Link Here ]
Additional Info/Tasks:
[ Email sent from Rosie Mae Bradshaw Link Here ]

## Project_Workflow
Project Workflow
Milestone | Task | Stage | Status | Deliverables | Stakeholder | Timeframe/Duration | Dependencies | Comments | Resources Required | Risk Assessment | KPIs | Communication Plan | Review Points | Budget Est. | Approval Requirements
1 | Establish structure for project workflow (PACE) | Plan | Completed | PACE Workflow Document - Project Scope and objectives outline, Initial project Timeline and milestone chart | Willow Jaffey (DS Lead), Rosie Mae Bradshaw (DS Manager) | 1-2 days | None |  | *Data team, Project management tools* | *Misalignment in scope; Ensure clear objectives* | *Workflow document completeness* | *Email updates, kickoff meeting* | *Initial review after setup* | *$500* | *Approval from DS Manager and Lead*
1a | Write a project proposal | Plan | Completed | Project Proposal Document - List of stakeholders and their roles, Approval from the executive team | Mary Joanna Rodgers (PM Officer) | 1 day | Establish structure | Project Proposals/Workflow are more complicated than they need to be. Once this is over, simplify the whole process and create a template for future projects | *Project documentation tools* | *Incomplete proposal; Assign experienced writers* | *Timely completion, accuracy of roles list* | *Weekly progress meetings, proposal review* | *Review after draft completion* | *$200* | *Executive team approval*
2 | Compile summary information about the data | Analyze | Completed | Comprehensive Data Summary Deport - Identified key features and variables | Orion Rainier (Data Scientist) | 1 day | Project proposal | Incorporate this summary within the Executive Summary | *Data access, Analytical tools (Python, R)* | *Data quality issues; Implement data validation* | *Accuracy and completeness of data summary* | *Bi-weekly data team meetings* | *Mid-point review of data summary* | *$1,000* | *Data team lead approval*
2a | Begin exploring the data | Analyze | Completed | Executive Summary - A preliminary data overview report, Initial data summary statistics, initial insights and patterns document | Orion Rainier (Data Scientist) | 1 day | Compile summary info | Keep it simple. Focus on key metrics. Full EDA is not required just yet | *Analytical tools (Python, R), Data access* | *Misinterpretation of data; Peer review findings* | *Number of insights and patterns identified* | *Weekly data exploration updates* | *Review of initial insights and patterns* | *$800* | *Data scientist lead review*
3 | Full EDA and cleaning | Analyze | In Progress | Cleaned Dataset - including cleaning log documentation. EDA Executive Summary - include Tableau visualizations and dashboards to effectively engage and communicate results to stakeholders | Orion Rainier (Data Scientist) | 1-3 days | Data exploration |  | *Data cleaning tools (Python, R), Data storage* | *Incomplete cleaning; Establish cleaning protocols* | *Quality and completeness of cleaned data* | *Daily status reports, Cleaning progress meeting* | *Final review after cleaning completion* | *$1,200* | *Data team lead approval*
3a | Visualization building | Construct | In Progress | Visualization Assets - graphs, charts, Interactive data dashboards | Mary Joanna Rodgers (PM Officer) | 1 week | Data exploration and cleaning |  | *Visualization tools, Data access* | *Misleading visuals; Validate accuracy* | *Accuracy and clarity of visualizations* | *Weekly visualization review meetings* | *Review of visualization drafts* | *$700* | *Project manager approval*
4 | Compute descriptive statistics | Analyze | Not Started | Descriptive Statistics Report - Data distribution visualizations, Analysis of testing results between two important variables | Willow Jaffey (DS Lead) | 1 week | Data cleaning |  | *Analytical tools (Python, R)* | *Errors in statistics; Double-check calculations* | *Correctness of descriptive statistics* | *Weekly statistics review meetings* | *Review of descriptive statistics* | *$400* | *DS lead approval*
4a | Conduct hypothesis testing | Analyze and Construct | Not Started | Hypothesis Testing Results Report - Recommendations for feature selection | Orion Rainier (Data Scientist) | 1 week | Descriptive statistics |  | *Analytical tools (Python, R), Statistical tools* | *Incorrect assumptions; Validate hypotheses* | *Validity of hypotheses* | *Bi-weekly hypothesis testing review* | *Review of hypothesis testing results* | *$500* | *Data team lead approval*
5 | Build a regression model | Analyze and Construct | Not Started | Initial Regression Model Model Performance Evaluation Report | Willow Jaffey (DS Lead) | 1-2 weeks | Hypothesis testing |  | *Analytical tools (Python, R), Regression tools* | *Model performance issues; Regular reviews* | *Model performance metrics* | *Weekly model review meetings* | *Review of initial regression model* | *$1,500* | *DS lead approval*
5a | Evaluate the model | Execute | Not Started | Model Evaluation Report - Identify areas for improvement | Rosie Mae Bradshaw (DS Manager) | 1-2 weeks | Build a regression model |  | *Model evaluation tools, Analytical tools (Python, R)* | *Model inaccuracies; Continuous monitoring* | *Improvement areas identified* | *Model evaluation review meetings* | *Review of model evaluation* | *$1,000* | *DS manager approval*
6 | Build a machine learning model | Construct | Not Started | Model Architecture Documentation Final Model | Willow Jaffey (DS Lead) | 1-2 weeks | Evaluate the model |  | *Analytical tools (Python, R), Model building tools* | *Overfitting; Regular model evaluation* | *Model accuracy and robustness* | *Weekly model development updates* | *Final model review* | *$2,000* | *DS lead approval*
6a | Communicate final insights with stakeholders | Execute | Not Started | Report to all Stakeholders Final Insights Presentation Stakeholder Feedback Report | Data team, TikTok executives | 1-2 weeks | Build a machine learning model |  | *Presentation tools, Reporting tools* | *Stakeholder disagreement; Frequent updates* | *Stakeholder feedback and satisfaction* | *Stakeholder feedback sessions* | *Final insights presentation review* | *$1,000* | *Executive team and data team approval*

## Project_Proposal
Project Proposal
Project Proposal Summary
Overview: This project proposal outlines a 12-week initiative to develop a machine learning model for classifying user interactions on TikTok as claims or opinions. This project aims to enhance content moderation efficiency, reduce user report backlogs, and improve overall user experience. The execution involves collaboration between the data team, cross-functional members, and TikTok executives.
[ Full Document Link Here ]
1. Planning Phase (1 week):
Establish project workflow structure (PACE).
Write detailed project proposal.
Define project scope, objectives, and initial timeline.
2. Data Analysis Phase (1 week):
Compile summary information about the data.
Begin data exploration.
3. Full EDA and Data Cleaning (1-2 weeks):
Clean and preprocess data.
Build and share visualizations.
4. Data Modeling Phase (2 -3 weeks):
Compute descriptive statistics.
Conduct hypothesis testing.
5. Model Development Phase (2-3 weeks):
Build initial regression model and evaluate performance.
Evaluate the model
6. Model Development and Final Presentation (1-2 weeks):
Build and optimize the machine learning model.
Communicate final insights to stakeholders.
Key Stakeholders:
Willow Jaffey (DS Lead)
Rosie Mae Bradshaw (DS Manager)
Mary Joanna Rodgers (PM Officer)
Orion Rainier (Data Scientist)
TikTok executives and other cross-functional team members.
Deliverables:
PACE workflow document.
Detailed Project Proposal.
Executive Summary Report.
Cleaned dataset
EDA executive summary
Visualizations and dashboards.
Descriptive statistics report
Hypothesis testing results.
Machine learning model and evaluation reports.
Final project presentation and stakeholder feedback report.

## C2_Tasks
Course 2: Understand the Data
Course 2 Assignment:
Build a dataframe for the claims classification data. After the dataframe is complete, organize the claims data for the process of exploratory data analysis, and update the team on your progress and insights through an executive summary.
| Action Items: |  | Comments:
| Install Packages and load TikTok csv file | Completed | Investigate the variables in the TikTok dataset to understand the distribution and engagement trends associated with the claim status and author ban status
| Build a dataframe for the TikTok dataset | Completed | Create a Dataset Dictionary
| Inspect Dataset | Completed | Create an Activity Log
| Compile summary information about the data | Completed | Enter Comments Here
| Gather descriptive statistics and begin initial EDA | Completed | Finish Answers to questions
| Visualize the TikTok data in Python | Completed | [ Completed Jupyter Notebook Link Here ]
| Report to TikTok’s data team through an executive summary | Completed | [ Completed Executive Summary Link Here ]
Additional Items/Tasks:
[ Email sent from Rosie Mae Bradshaw Link Here ]
Action Items:
TRUE | Review the attached dataset in the Jupyter notebook.
TRUE | Complete the coding required to prepare the data.
TRUE | Organize the notebook for EDA.
TRUE | Coordinate with Orion Rainier for any specific details or instructions needed.
[ Email sent from Orion Rainer Link Here ]
Action Items:
TRUE | Import and inspect the dataset in the Jupyter notebook.
TRUE | Summarize the column data types and non-null counts.
TRUE | Column data types.
TRUE | Data value non-null counts.
TRUE | Relevant and irrelevant columns.
TRUE | Any noteworthy code-related observations.
TRUE | Identify relevant and irrelevant columns.
TRUE | Select key variables and analyze their min and max values.
TRUE | Create and document meaningful variables.

## Dataset_Dictionary
Dataset Dictionary
Column name | Type | Description
# | int | TikTok assigned number for video with claim/opinion.
claim_status | obj | Whether the published video has been identified as an “opinion” or a “claim.” In this dataset, an “opinion” refers to an individual’s or group’s personal belief or thought. A “claim” refers to information that is either unsourced or from an unverified source.
video_id | int | Random identifying number assigned to video upon publication on TikTok.
video_duration_sec | int | How long the published video is measured in seconds.
video_transcription_text | obj | Transcribed text of the words spoken in the published video.
verified_status | obj | Indicates the status of the TikTok user who published the video in terms of their verification, either “verified” or “not verified.”
author_ban_status | obj | Indicates the status of the TikTok user who published the video in terms of their permissions: “active,” “under scrutiny,” or “banned.”
video_view_count | float | The total number of times the published video has been viewed.
video_like_count | float | The total number of times the published video has been liked by other users.
video_share_count | float | The total number of times the published video has been shared by other users.
video_download_count | float | The total number of times the published video has been downloaded by other users.
video_comment_count | float | The total number of comments on the published video.

## C3_Tasks
Course 3: EDA
Assignment Goal:
Initiate and complete the exploratory data analysis (EDA) process for the claims classification project. Additionally, use Tableau to create visualizations that will be included in an executive summary, enabling non-technical stakeholders to effectively engage with and understand the data.
| Action Items: |  | Comments:
| Create Jupyter Notebook, Upload Data and relelvant libraries/packages | In Progress | Top 3 items required in Jupyter Notebook
| Data Structuring, Cleaning, and Validation | In Progress | Remember create the 3 additional columns
| Perform EDA and Create Python Visualizations | In Progress | [ Completed Jupyter Notebook Link Here ] How do I upload Notebook to Github or online for people to see?
| Create Data Visualizations in Tableau | Not Started | Following 3 items in Tableau
| Build Dashboard and Publish on Tableau Public | Not Started | [ Completed Tableau Dashboard Link Here ] See email requests for details. Also remember to account for visually impaired team member (TikTok brand colours are difficult to see side by side for those who are colour blind). Post Dashboard link here
| Create and Present Executive Summary using Canva | Not Started | [ Completed Executive Summary Link Here ]
Additional Items/Tasks:
[ Email from Orion Rainer, Data Scientist Link Here ]
Action Items:
TRUE | Confirm if Rosie Mae Bradshaw has informed you what the management team expects regarding the EDA.
FALSE | Show your work in a Python notebook, including:
FALSE | - Structuring and cleaning the data.
FALSE | - Visualizations using matplotlib/seaborn, specifically:
FALSE | - A graph comparing claim counts to opinion counts.
FALSE | - Boxplots of key variables ("video duration," "video like count," "video comment count," "video view count") to check for outliers.
FALSE | - A breakdown of "author ban status" counts.
FALSE | Include Tableau visualizations in the EDA, specifically:
FALSE | - A Tableau dashboard showing a simple claims versus opinions count.
FALSE | - Stacked bar charts of claims versus opinions for variables like video view counts, video like counts, video share counts, and video download counts.
FALSE | - Ensure the visualizations are easy to understand for non-technical stakeholders.
FALSE | - Consider that the assistant director has visual impairments.
FALSE | Confirm if you need any help with the Tableau visualizations.
[ Email from Willow Jaffey, DS Lead Link Here ]
Action Items:
FALSE | Create an Executive Summary of your analysis attached via email.

## Activity_Log
Activty Log
Course | Stage | Activity | Actions | Insights
2 | Analyze | Install Packages and load TikTok csv file | Imported necessary packages - import pandas as pd - import numpy as np Loaded dataset into dataframe - data = pd.read_csv("tiktok_dataset.csv")
2 |  | Build a dataframe for the TikTok dataset Inspecting Data Compile summary information about the data | Used the data.head(10), data.info(), and data.describe() functions to inspect the data | - The dataframe includes a mix of categorical, text, and numerical data, where each row represents a distinct TikTok video. It captures the claim status of the video along with various video metrics, such as video ID, duration, view count, transcript, verification status, and ban status. - data contains 19,382 entries, 12 columns, dtypes = fivefloat64s, three int64s, and four objects - 7 columns with 298 missing entries - Looking at the mean vs median values along with some high standard deviations in the numerical columns indicate the presence of outliers
2 |  | Distribution of Claim Status | Used the value_counts() function to determine the number of claims vs opinions | - relatively even distribution of 9608 Claims vs 9476 Opinions
2 |  | Examine Engagement Trends by Claim Status | Calculated the mean and median values of both Claims and Opinion statuses | Mean Claims: 501029.4527477102 Median Claims: 501555.0 Mean Opinions: 4956.43224989447 Median Opinions: 4953.0 - The mean and median values are relatively balanced per category; however, there is a more than 100-fold difference in mean/median view counts between the claims and opinions.
2 |  | Analyze Trends by Author Ban Status | Caculated the number of videos for each combination of categories of claim status and author ban status Note: Exemplar code is a little simpler - data.groupby(['claim_status','author_ban_status']).count()[['#']] | - Active author numbers are predominant in both claim statuses. - However, there is a significant difference: those in the claim category have a much higher number of banned and under-review statuses compared to those in the opinion category. - This could suggest that the moderation efforts might be more stringent for claims, indicating that claims are more likely to be flagged for review or result in author bans.
2 |  | Investigate Engagement Levels by Author Ban Status | Caculated the median video share count of each author ban status Used the groupby() and agg() functions to calculate the count, mean, and median of each of the following variables video views, video likes, and video shares. | - Banned authors have significantly higher video share counts than others at nearly 60%. Combined, banned and under-review statuses account for 98.2% of all video share counts. - Banned authors have high engagement, indicating their content garners significant attention. - Banned (29,998) and under review (25,774) authors have higher mean video share counts than active authors (14,111), suggesting more frequent sharing due to potentially controversial content. - Despite being fewer in number (1,635 banned and 2,066 under review vs. 15,383 active), banned and under review authors have much higher average engagement metrics, indicating a potentially impactful minority.
2 |  | Create Engagement Rate Columns and calculate the mean, median, and counts for each | Created 3 new columns likes_per_view: represents the number of likes divided by the number of views for each video comments_per_view: represents the number of comments divided by the number of views for each video shares_per_view: represents the number of shares divided by the number of views for each video Grouped and aggregated new columns to achieve activity Imported matplotlib.pyplot and seaborn to create heatmaps and a bar chart to inspect trends further | - Videos from banned and under review authors generally get more views, likes, and shares compared to videos from active authors. - When a video is viewed, its engagement rate (likes, comments, shares per view) is more related by whether it is a claim or an opinion rather than the author's ban status. - Claim Videos: These videos are generally more engaging in terms of likes, comments, and shares, especially for banned authors. This suggests that claim videos, especially from banned authors, tend to attract more positive attention. - Opinion Videos: Active and under review authors perform better in terms of engagement rates compared to banned authors.
2 |  | Summarize Findings | Summarize all insights into a clear and concise format to present to Rosie Mae Bradshaw and TikTok data team Create Executive Summary Report in Canva - Requires tables of data made for Canva Data Viz's | Percentage of Claims and Opinions: - Claims: 49.6% (9608 videos) - Opinions: 48.9% (9476 videos) - Missing entries: 1.5% (298 entries out of 19,382 total) Core Insight: Factors Correlating with a Video's Claim Status: - Claim videos are more likely to be flagged for review or result in author bans, with banned authors having higher engagement metrics (likes, comments, shares). Core Insight: Factors Correlating with a Video's Engagement Level: - Videos from banned and under-review authors have significantly higher engagement (views, likes, shares) compared to active authors, indicating that controversial content garners more attention.
3

## C4_Tasks
Course 4:
Assignment Goal:
| Action Items: |  | Comments:
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
Additional Info/Tasks
FALSE

## C5_Tasks
Course 5:
Assignment Goal:
| Action Items: |  | Comments:
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
Additional Info/Tasks
FALSE

## C6_Tasks
Course 6:
Assignment Goal:
| Action Items: |  | Comments:
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
| Enter Action Item Here | Not Started | Enter Comments Here
Additional Info/Tasks
FALSE